## Sheet1
Sprint Start Date | 1/11/2021 | Day of sprint | forecast | Target | Total effort per day | Actual
Sprint End Date | 2021-01-18 | 0 | 144 | 192 | 0 | 192
Working Days | 8 | 1 | 126 | 168 | 24 | 168
Team Size | 4 | 2 | 108 | 144 | 15 | 153
Work Hours per Day | 6 | 3 | 90 | 120 | 21 | 132
Total Available Hours | 192 | 4 | 72 | 96 | 21 | 111
Average Daily Available Hours | 24 | 5 | 54 | 72 | 21 | 90
Average Productivity % | 80% | 6 | 36 | 48 | 30 | 60
Productive Hours | 144 | 7 | 18 | 24 | 30 | 30
Average Daily Productive Hours | 18 | 8 | 0 | 0 | 30 | 0
Sprint 2 | Points | Assigned
Tree Chart | 21 | Charlie
WeChat in the media | 5 | Vonti
Imbedded narrative headlines and subtitles #38 | 5 | Hugo
Make links to specific datasets explicit #39 | 3 | Vonti
Contact us | 3 | Ciel
End single scroll | 34 | Ciel
Headline formatting to clarify section breaks #44 | 5 | Charlie
Re-Order Sections to Retain Focus on Censorship rather than WeChat #45 | 8 | Vonti
Provide text based context for figures/graphs #46 | 13 | vonti and Hugo
Utilize Agile Scrum #6 | 8 | Team
Accesibility | 8 | Ciel
Readability | 8 | Vonti
Web Design (Aesthetics) #13 | 21 | Ciel
Citations | 8 | Victoria and Ciel
Histogram | 21 | Hugo
Data for tree chart | 21 | Victoria and Ciel
Total points Sprint 2 | 192